## Burn Down Chart
Projected BurnDown
| Week 9 W | Week 9 F | Week 10 M | Week 10 W | Week 10 F | Week 11 M | Week 11 W | Week 11 F | Week 12 M | Week 12 W | Week 12 F | Week 13 M
| 2020-11-18 | 2020-11-20 | 2020-11-23 | 2020-11-25 | 2020-11-27 | 2020-11-30 | 2020-12-02 | 2020-12-04 | 2020-12-07 | 2020-12-09 | 2020-12-11 | 2020-12-14 | NOTES
Project Planning | 2020-11-18: Michelle and Ciaran; 2020-11-23: Everyone (Melissa Lead) | Create Project outline
Ticket Booking System | 2020-11-25: Melissa; 2020-12-07: (Polish) | Start the main file
Plane | 2020-11-25: Melissa | Create and test plane
Abstract Passenger | 2020-11-25: Ciaran | Create passenger, test passenger
Adult | 2020-12-02: Ciarn | Create and test Adult
Child | 2020-12-02: Michelle | Create and test Child
Senior | 2020-12-02: Michelle | Create and test Senior
Project Documentation | 2020-11-25: Everyone (Michelle Lead) | Create UML document and how-to-use-program document
Write up | 2020-12-07: Everyone (Michelle Lead) | Create write up
Presentation Prep | 2020-12-09: Everyone (Melissa Lead) | Create and practice presention
Presentation | 2020-12-14: Everyone | Present
Actual BurnDown
| Week 9 W | Week 9 F | Week 10 M | Week 10 W | Week 10 F | Week 11 M | Week 11 W | Week 11 F | Week 12 M | Week 12 W | Week 12 F | Week 13 M
| 2020-11-18 | 2020-11-20 | 2020-11-23 | 2020-11-25 | 2020-11-27 | 2020-11-30 | 2020-12-02 | 2020-12-04 | 2020-12-07 | 2020-12-09 | 2020-12-11 | 2020-12-14 | Notes
Project Planning | 2020-11-18: Michelle and Ciaran; 2020-11-23: Everyone (Melissa Lead); 2020-12-07: Projected Deadline | Melissa didn't join until Week 10 Monday
Ticket Booking System | 2020-12-07: Projected Deadline
Schedule Planes | 2020-12-07: Projected Deadline | Added a class to better care for the scheduling
Plane | 2020-11-25: Melissa; 2020-12-07: Projected Deadline
Abstract Passenger | 2020-11-25: Ciaran; 2020-12-07: Projected Deadline
Adult | 2020-12-07: Projected Deadline
Child | 2020-12-07: Projected Deadline
Senior | 2020-12-07: Projected Deadline
Project Documentation | 2020-11-25: Everyone (Michelle Lead); 2020-12-07: Projected Deadline
Write up | 2020-12-07: Projected Deadline
Presentation Prep | 2020-12-04: Check-in Rosaleen; 2020-12-07: Projected Deadline
Presentation | 2020-12-07: Projected Deadline

## Checklists
Code |  | Write Up |  | UML |  | Powerpoint
Completed | Item | Completed | Item | Completed | Item | Completed | Item
| Encapselation |  | Intro and outline of team members |  | TicketBookingSystem |  | Intro and outline of team members
| Abstraction |  | Methods |  | Plane |  | Methods
x | Lists |  | Analysis requirements |  | SchedulePlanes |  | Analysis requirements
| File Reading |  | Prep sheets and uml |  | Passenger |  | Prep sheets and uml
| File Writing |  | Implemntation |  | Adult |  | Implemntation
x | Error Handling |  | Testing Strategy |  | Child |  | Testing Strategy
| Input |  | Interpretation of user requirements |  | Senior |  | Interpretation of user requirements
| Output |  | Sutiability |  |  |  | sutiability
| Inheritance |  | Features |  |  |  | Features
x | Structure |  | Future Improvements |  |  |  | Future Improvements
Documentation (how to)
Comments
Descriptive variables
x | Public Method
x | Protected Method
x | Private Method
x | toString
Superclass (use an abstract)
x | Future Improvements (excel)

## Sprint Discussion
Date | Michelle: Done | Michelle: ToDo | Ciaran: Done | Ciaran: ToDo | Melissa: Done | Melissa: ToDo | Group Plan for next Discussion
2020-11-25 | Started Project Plan, Created The Trello | Add Melissa To Trello, join Github Project | Started Project Plan | Download GitHub Desktop and Create Abstract Passenger | Created Documents, Started a project outline in github | Start the Plane class | Finsh ToDos, Finish adding everything to the checklists tab (flesh out project requirements and what we have already)
2020-11-30 | Began working on the write up | Begin the UMLs | Created Passenger (not abtract) | Make Passenger Abstract, start Adult | Most of the Plane class completed, wait on Adult class to finish off. Also began a scheduling class. | Finish the Scheduling Class by being able to load from saved document | Actually get everyone together in the same virtual room and begin to put the code together in one document. And take a look at what we have written up so far.
2020-12-02 | Continued Working on the Write up, Worked on a few of the UMLS | Continue with Write up and UMLs | Passenger Class finished - to be turned abstact | Make Passenger Abstract, work on adult (possibly using the this() and super() constructors) | Fixed errors with the pricing in the plane class, added the ability to print out all available seats and updated documents and commented code. | Work on the save/load of the schedule | Set up a meeting with Rosaleen to ensure we are on track
2020-12-04 |  |  | Continued working on making Passenger Abstract and working on Adult | Continue working on Passenger and Adult Classes | Continued working on the save/load of the schedule | Continue working on Plane and Schedule classes - Also expanding on the methods document to help show how each class works | We had a discussion with Rosaleen to make sure that we fully understood what was needed and ensured that we are on the right track.
2020-12-07 | [6 empty] | (Planned) Team Tackle the TicketBookingSystem class on Tuesday at 12:00 lunch time
2020-12-09
2020-12-11
2020-12-14

## Future Directions
Schedule/Plane: Departure Time
Schedule/Plane: Delays
Schedule/Plane: Arrival Time
Plane: Destination
Plane: Departure Place
Plane: Use this as an Abstract class and have Child classes of different plane types.