## Burn Down Chart
Projected BurnDown
| Week 9 W | Week 9 F | Week 10 M | Week 10 W | Week 10 F | Week 11 M | Week 11 W | Week 11 F | Week 12 M | Week 12 W | Week 12 F | Week 13 M
| 2020-11-18 | 2020-11-20 | 2020-11-23 | 2020-11-25 | 2020-11-27 | 2020-11-30 | 2020-12-02 | 2020-12-04 | 2020-12-07 | 2020-12-09 | 2020-12-11 | 2020-12-14 | NOTES
Project Planning | 2020-11-18: Michelle and Ciaran; 2020-11-23: Everyone (Melissa Lead) | Create Project outline
Ticket Booking System | 2020-11-25: Melissa; 2020-12-07: (Polish) | Start the main file
Plane | 2020-11-25: Melissa | Create and test plane
Abstract Passenger | 2020-11-25: Ciaran | Create passenger, test passenger
Adult | 2020-12-02: Ciarn | Create and test Adult
Child | 2020-12-02: Michelle | Create and test Child
Senior | 2020-12-02: Michelle | Create and test Senior
Project Documentation | 2020-11-25: Everyone (Michelle Lead) | Create UML document and how-to-use-program document
Write up | 2020-12-07: Everyone (Michelle Lead) | Create write up
Presentation Prep | 2020-12-09: Everyone (Melissa Lead) | Create and practice presention
Presentation | 2020-12-14: Everyone | Present
Actual BurnDown
| Week 9 W | Week 9 F | Week 10 M | Week 10 W | Week 10 F | Week 11 M | Week 11 W | Week 11 F | Week 12 M | Week 12 W | Week 12 F | Week 13 M
| 2020-11-18 | 2020-11-20 | 2020-11-23 | 2020-11-25 | 2020-11-27 | 2020-11-30 | 2020-12-02 | 2020-12-04 | 2020-12-07 | 2020-12-09 | 2020-12-11 | 2020-12-14 | Notes
Project Planning | 2020-11-18: Michelle and Ciaran; 2020-11-23: Everyone (Melissa Lead); 2020-12-07: Projected Deadline | Melissa didn't join until Week 10 Monday
Ticket Booking System | 2020-12-07: Projected Deadline
Plane | 2020-11-25: Melissa; 2020-12-07: Projected Deadline
Abstract Passenger | 2020-11-25: Ciaran; 2020-12-07: Projected Deadline
Adult | 2020-12-07: Projected Deadline
Child | 2020-12-07: Projected Deadline
Senior | 2020-12-07: Projected Deadline
Project Documentation | 2020-11-25: Everyone (Michelle Lead); 2020-12-07: Projected Deadline
Write up | 2020-12-07: Projected Deadline
Presentation Prep | 2020-11-27: Check-in Rosaleen; 2020-12-02: Check-in Rosaleen; 2020-12-07: Projected Deadline
Presentation | 2020-12-07: Projected Deadline

## Checklists
Code |  | Write Up |  | UML |  | Powerpoint
Completed | Item | Completed | Item | Completed | Item | Completed | Item
| Encapselation |  | Intro and outline of team members |  |  |  | Intro and outline of team members
| Abstraction |  | Methods |  |  |  | Methods
| Lists |  | Analysis requirements |  |  |  | Analysis requirements
| File Reading |  | Prep sheets and uml |  |  |  | Prep sheets and uml
| File Writing |  | Implemntation |  |  |  | Implemntation
| Error Handling |  | Testing Strategy |  |  |  | Testing Strategy
| Input |  | Interpretation of user requirements |  |  |  | Interpretation of user requirements
| Output |  | Sutiability |  |  |  | sutiability
| Inheritance |  | Features |  |  |  | Features
| Structure |  | Future Improvements |  |  |  | Future Improvements
Documentation (how to)
Comments
Descriptive variables
Public Method
Protected Method
Private Method
toString
Superclass (use an abstract)
x | Future Improvements (excel)

## Sprint Discussion
Date | Michelle: Done | Michelle: ToDo | Ciaran: Done | Ciaran: ToDo | Melissa: Done | Melissa: ToDo | Group Plan for next Discussion
2020-11-25 | Started Project Plan, Created The Trello | Add Melissa To Trello, join Github Project | Started Project Plan | Download GitHub Desktop and Create Abstract Passenger | Created Documents, Started a project outline in github | Start the Plane class | Finsh ToDos, Finish adding everything to the checklists tab (flesh out project requirements and what we have already)
2020-11-27
2020-11-30
2020-12-02
2020-12-04
2020-12-07
2020-12-09
2020-12-11
2020-12-14

## Future Directions
Plane: departure time
Plane: delays
Plane: arrival time
Plane: destination